Carpenter Reconstruction Project:

Update as of 5/17/2024 - Project will start on 5/20/2024 Signage will be put out and detours will start to happen.

Watermain installation and sewer will start on Wednesday at Hamilton Avenue.

Kimberly road will be milled out on Monday and paved back shortly after.

7/23/2024 - Bacco continues to work on water, strom, and sanitary on the south bound lane on Carpenter Ave. Northbound will be for northbound traffic all south bound traffic will take the detour route down Kimberly to Hamilton back to Carpenter Ave.

9-6-2024 - 95% of the utilities will be done by middle of next week. There is a sewer on the Iron Mountain side to replace the Kingsford has a water connection to make which will complete all of the underground work. There are currently removing the Woodward and Carpenter intersection and should have that completed by the end of next week. After that road will be graveled and curbing and sidewalks will be installed. The anticipated completion date remains as September.

10/9/2024 - Work Complete